## Slide 1: List of outcome and actions (30.3.2023)
LECTURES
Action all: log into https://event.ipp-hgw.mpg.de/category/65/ and get back to andrea.kleiber@ipp.mpg.de if access does not work – the INDICO section will be the repository to exhcange infromaation for the lectures/book project
Agree on format (15+15 students?, 90‘+30‘, Speaker/Chairperson = Author Team) (agreed)
Action: the Coordination team will advertise 15 participation slots for students outside Ukraine (same academic level as expected Urkainian audience). The lecturers are invited to nominate students before a more public advertisment is made.
Action authors of individual chapters: will agree on role distribution (per lecture) and inform Andrea about the roles
Participants of the meeting agreed to record the lecture and to make it available to the participants of the lecture series
Clarification: The lectures will assume that the participants hold a Bachelor degree and have a background in general physics.
Agree on time-lime for lectures (two tentative options
Action: Igor and Igor discuss with Ukrainian participants the schedule options (two scenarios in excel file) and get bacl to Andrea at their earliest convenience. The coordination team will communicate with the lecturers the schedule.
DINKLAGE | The Stellarator Concept – The Charkiw Lectures| VC - April 3, 2023 | Page 1

## Slide 2: List of outcome and actions (30.3.2023)
Book Project
Action Editorial Team: create a document with guidelines and provide a sample chapter as an example.
Action all: individual lessons/chapters produce a list of content and make prerequisites explicit (e.g. stellarator theory requires basic knowledge of MHD) – the list of content is uploaded on the INDICO page
Boundary condition: Agreed approach for the book project: figures will be delivered as a sketch or published version but with data and all material required for figures. All figures for the book project will be generated in a common style. Andrea is in charge.
Decision preference w.r.t. a publisher: keep in touch and wait for responses form IOPP and Springer
Action all: inform Andrea/Andreas about publisher preferences if not done
Discuss time-line for book project: rough time-line was agreed to be realistic but is subject to individual arrangements. The authors are kindly requested to inform the coordination team if any deviations to the planning should come up to find individual solutions.
Action Andreas/Andrea: revision and communication of time-line after feed-back from Igor and Igor
DINKLAGE | The Stellarator Concept – The Charkiw Lectures| VC - April 3, 2023 | Page 2